## 📅 Timeline Planner
Shopify Migration Timeline Planner — eCommerce Development Pros
Enter your project start date and estimated days per phase to generate a realistic migration schedule
Phase | Min Days | Max Days | Your Est. Days | Start Date | End Date | Risk Level | Notes / Dependencies
1. Audit & Planning | 2 | 5 | 3 | 2026-06-01 | 2026-06-03 | Critical | Poor planning leads to delays in every subsequent phase
2. Store Setup & Design | 5 | 12 | 7 | 2026-06-04 | 2026-06-10 | Very High | Design revisions and stakeholder approval are the #1 timeline risk
3. Data Migration | 3 | 10 | 4 | 2026-06-11 | 2026-06-14 | High | Data quality directly determines how long this phase takes
4. SEO & Redirect Setup | 2 | 5 | 3 | 2026-06-15 | 2026-06-17 | Critical | URL mapping must be complete before redirects are implemented
5. Integrations Setup | 5 | 20 | 3 | 2026-06-18 | 2026-06-20 | Medium | ERP/CRM integrations can extend this significantly
6. Testing & QA | 3 | 5 | 3 | 2026-06-21 | 2026-06-23 | Critical | Do not compress QA to hit a launch date
7. Launch & Post-Launch | 1 | 3 | 2 | 2026-06-24 | 2026-06-25 | High | Monitor GSC and analytics closely for 30 days post-launch
TOTAL ESTIMATED DAYS | 21 | 60 | 25
PROJECT START DATE (enter below):
Start Date: | 2026-06-01
Formulas:
End Date = [Start Date]+[Your Est. Days]-1
Start Date = [End Date, row above]+1

## ⚠️ Risk Assessment
Migration Timeline Risk Assessment— eCommerce Development Pros
Risk Factor | Your Store Has This? | Timeline Impact | How to Mitigate | Priority
Large product catalog (5,000+ SKUs) |  | +2–4 weeks | Export and clean data before project starts. Remove duplicates, fix missing fields. | High
Messy or inconsistent product data |  | +1–3 weeks | Audit and standardise data format before handoff. Agree on data structure upfront. | Critical
Custom design (not pre-built theme) |  | +1–3 weeks | Finalise design direction and approval process on day one. Set firm review deadlines. | Very High
Multiple stakeholder approvals required |  | +1–2 weeks | Identify all approvers at project start. Set approval windows — not open-ended feedback. | High
ERP or CRM integration required |  | +1–3 weeks | Confirm Shopify-compatible solution or custom dev scope before project starts. | High
Migrating from Magento or custom platform |  | +1–2 weeks | Allow extra time for data mapping and URL redirect work. More manual effort required. | High
Large number of URLs to redirect (1,000+) |  | +3–5 days | Start URL mapping early. Use the Redirect Mapping Template to work in batches. | Medium
Scope not fully defined at project start |  | +Variable | Lock scope before any design or development starts. Document agreed features in writing. | Critical
Migrating close to a peak trading period |  | Schedule risk | Plan migration launch at least 6–8 weeks before peak season. Never migrate during peak. | Critical
No dedicated internal project contact |  | +1–2 weeks | Assign one internal owner who can make decisions and provide feedback quickly. | Medium